## Tasks
# | Group | Task | Status | Comments
2 | docs | Record video describing how to use the program
4 | docs | Write how to add new method in detail
6 | docs | Describe the format of data input files
7 | docs | Describe how to implement methods that require initialization
17 | docs | Write user manual describing user interface and symbols
18 | docs | Write examples and documentation for integration in most common languages (Matlab,Fortran, C/C++,Python)
20 | docs | Record video describing how to use the program
27 | docs | Write user manual describing user interface and symbols | IN PROGRESS
28 | docs | Write examples and documentation for integration in most common languages (Matlab, Fortran, C/C++) | DONE
3 | gui | Implement tooltips and online contextual help | IN PROGRESS
9 | gui | (POSTPONED) Dataset separation by fault types
10 | gui | Define combined datasets | DONE
12 | gui | Review listed methods and listed datasets and add their references (sherif & Ibrahim) | DONE
21 | gui | Display diagnosis as symbol | DONE
22 | gui | Add drop down list to choose method for displaying accuracy table | DONE
23 | gui | Edit row and column headings | DONE
25 | gui | Input file without ACT | DONE
31 | gui | Add export result graph and export result tables to package | DONE
32 | gui | Add GUI for adding new methods | DONE
33 | gui | Gasses that are not included take the value -1 and are not displayed | DONE
34 | gui | Edit config.xlsx from within the application to add/edit/remove methods (MATLAB methods, Standalone executable methods) | DONE
35 | gui | Edit config.xlsx from within the application to add/edit/remove data sets | DONE
36 | gui | Allow user to choose from predefined datasets or select an input file | DONE
37 | gui | Change the “GO” button to “Run” | DONE
38 | gui | Add "Enter" button to Configure Methods and Configure Datasets figures to save immediately | DONE
39 | gui | Add "OK" to save in Configure Methods and Configure Datasets | DONE
40 | gui | Hide the graph title after user hits "RUN" | DONE
42 | gui | Show progress bar for dataset analysis | DONE
43 | gui | Directly edit .m files from the method configuration window | DONE
1 | methods | (POSTPONED) Test integration of Simulink-based method
5 | methods | Consider allowing external methods to receive multiple points
24 | methods | Allow adding .exe to method function list | DONE
26 | methods | Test integration of Fortran-based method | DONE
30 | methods | Add ANN method to package | DONE
41 | methods | Recompile FORTRAN program to make sure it uses the proper input and output filenames and is properly LICENSED. | DONE
8 | paper | Data set documentation and references and demonstration of value
13 | paper | Retake all screenshot Figures
14 | paper | Add graphical results figures and comment on them
15 | paper | Comment on all Figures
16 | paper | Add appendix with sample implementation of a method
11 | www | Provide technical support contact form
19 | www | Provide technical support for users with other programming languages
29 | www | Upload package to github and make webpage to showcase the package | DONE
44 | gui | Transposed the Diagnosis Table | DONE
45 | gui | Fix ratio8_callback bug | DONE
46 | gui | Updated the progress slider | DONE
47 | gui | Added some tooltip strings to the DGA_UI figure | DONE
48 | gui | Put icons on the Dataset/Method add and remove buttons | DONE
49 | gui | Replaced the InputMode dropdown list with a radio button for simpler and more consistent user experience | DONE
50 | gui | Added warning message when an attempt to run DGA in the dataset input mode without selecting a dataset. | DONE
51 | gui | Allowed the user to choose file name and location for exported tables and graphs and warn before overwriting existing files. | DONE
52 | gui | Increased the font size for exported graph and replaced diagnosis codes with the corresponding symbols | DONE
44 | gui | Refactoring ExportView code | DONE